## Slide 1
1 · TAKING OWNERSHIP OF THE AGREED PATHWAY
Own the agreed pathway without stalling it: understand, stabilise, accelerate
VALUE
TIME
Publishing model
today
Digital product platform
the agreed direction
Inflection point
The pivot — agreed
fixed target date
Understand
DAYS 1–30
two baselines: the technology and the ways of working
Stabilise
DAYS 31–60
keep today running; assess the proposal; confirm, re-scope or stop
Accelerate
DAYS 61–90 →
first assured delivery; the plan to the date
Every design and staffing statement that follows is a hypothesis. Gates 1 and 2 test it before anything is built.
Nothing that works today stops until its replacement is proven.
Notes: Slide 1: Own it without stalling it
Pathway agreed, date fixed: own it, don’t stall it
Publishing model → digital product platform; pivot agreed, shape and ways of working not
Understand 1–30 (two baselines) · Stabilise 31–60 (keep running, assess proposal, confirm/re-scope/stop) · Accelerate 61–90→ (first assured delivery, plan to date)
Rule 1: nothing that works stops until replacement proven. Rule 2: nothing starts without owner and gate
Say it: everything after this is a hypothesis; Gates 1 and 2 test it
Story: inherited mid-flight
Bridge: “Here’s that on the calendar.”

## Slide 2
2 · THE FIRST 90 DAYS AGAINST THE 27 APRIL DATE
A December start leaves little room: three gates by early March, then eight weeks to go live
December break
Dec
Jan
Feb
Mar
Apr
Start
G1
Day 30
Two baselines
G2
Day 60
Fit test, decisions
G3
Day 90
First assured delivery
27 April
fixed
≈ 8 working weeks after day 90: build waves, rehearsal, go-live
Technology and product baseline
Systems, integrations, contracts, partners, run cost; licence model; what is in flight
Ways-of-working baseline
Processes, SOPs, SLAs, mandated requirements; hand-offs; what each ceremony produces
The fit test — at Gate 2
Does the proposal support the way we want to work?
Is each component in the right tier, under the right rule?
THE REALITY: PROTECT WHAT WORKS, AND HOLD THE SCOPE
Start in December
The break takes three of the first four weeks; Gate 1 lands mid-January in practice, so the baselines are a fortnight of work, not a month
Day 90 is early March
About eight working weeks remain for build waves, a cutover rehearsal and go-live before 27 April
Don’t break what is working
Nothing that works today stops until its replacement is proven; in-flight work is confirmed or stopped by Gate 1
Work with the team in place
The plan assumes the people and partners we have; new hires or proposals are not baked into it
Scope is the only lever
No growth on hoped-for AI or efficiency gains, no slippage on quality or risk; what does not fit moves to Day 1.5
Decide early, in writing
Any scope-versus-date trade-off goes to the board at Gate 2, in late January — not in April
Notes: Slide 2: 90 days vs 27 April
December start; break eats 3 of first 4 weeks; Gate 1 mid-Jan; baselines = a fortnight
Day 90 early March; about 8 working weeks to go-live
G1 day 30: two baselines → one-page baseline, in-flight list
Why two: proposal = technology and products, not how we work; savings live there
G2 day 60: fit test (supports how we work? right tier, right rule?) → the plan we’re held to. Builds on Phase 1 assurance review
G3 day 90: first assured delivery (identity and entitlement, or content pipeline)
Not in 90 days: commit to architecture, migrate data, extra hires, refined date or cost, AI platform before governance
Scope is the only lever; trade-off to board at G2, late Jan, in writing
Story: fixed date
Bridge: “Next three slides: one credible shape the assessment would weigh, not the answer.”

## Slide 3
3 · HOW GATE 2 ASSESSES EACH COMPONENT
Four questions per component: what it is decides where time, money and concern go
ILLUSTRATIVE — NOT A DECISION
1
What kind of thing is it?
2
Spending judged on?
3
How resilient?
4
Build or buy?
OPTIONAL UPLIFT
Where AI helps
A
AMH Online — web, desktop, mobile, and the APIs into third-party systems
Commercials, opportunity, strategy
Bullet-proof: life-critical content
Build: strong appetite to wrap our own technical solutions
+
Accelerate and de-risk product work
B
Quark Content and PriXM — authoring and publishing
Fit for authors, portability, cost
Business hours; never the only copy
Buy and configure: plugins, paid features, small code where it pays
+
Author assistance; human sign-off
C
D365 / Dataverse, WooCommerce shop, D365 internal shop, Wiise, Power BI
Cost and effort vs efficiency gained
Standard; no shared fate
Buy: standard set-up; deviate by exception only
+
Woven into process; must-haves shrink
X
Azure identity and access plane, API gateway / service bus, monitoring, ISMS and standards
Inherits, plus risk and reputation
Inherits A wherever it sits in A’s path
Buy, but bend to accommodate A and third parties
+
Review, triage, runbooks
Notes: Slide 3: Four tiers, four questions
Four questions: what kind of thing / spending judged on / how resilient / build or buy
A product (AMH Online): moat · commercials · bullet-proof · build
B content tooling (Quark, PriXM): content is the asset · fit, portability, cost · business hours, never only copy · buy and configure
C commodity (D365, shop, Wiise, Power BI): cost vs efficiency · standard, no shared fate · buy, exceptions only
X cross-cutting (identity, bus, monitoring, ISMS): inherits A’s posture · buy, bend to A
AI: A accelerates · B assists, human sign-off · C woven in (Excel pricing step) · X triage and runbooks
Guardrail: no AI output to content or production without a human gate
Story: commodity over build (CRM)

## Slide 4
4 · THE RESILIENCE TOOLKIT, BY TIER
Five kinds of protection: in full for the five-nines product, proportionate for the rest
ILLUSTRATIVE — NOT A DECISION
1 · Isolate
no shared fate
Hub and spoke; commodity behind the bus
A
X
C
Published content at the edge (CDN)
A
Entitlements cached, with grace
A
X
Read-only degraded mode
A
Bulkheads, circuit breakers, back-pressure
A
X
2 · Replicate
no single point
Active-active across regions
A
X
Stateless services, replicated data
A
X
Identity-provider outage plan
A
X
SaaS and vendor failover plans
A
B
C
Capacity headroom and load testing
A
X
3 · Release safely
no big-bang change
Feature switches — ship dark, release deliberately
A
Blue/green deployment
A
Canary by cohort, automated rollback
A
Configuration changes versioned and staged
A
B
C
Immutable, versioned content releases
A
B
4 · Detect and respond
minutes, not hours
SLOs and error budgets
A
Synthetic checks from customer locations
A
X
Runbooks; 24×7 on-call via MSP
A
X
C
Status page and incident comms
A
X
B
C
Game days and DR drills (RTO/RPO)
A
X
C
5 · Protect content
integrity above all
Content checksums and integrity checks
A
B
Copies held outside the authoring tool
A
B
Replay from the bus after outages
A
C
Backups and restore drills for CRM, shop, finance
A
C
Audit trail: what changed, when, who
A
B
C
Badges show which tiers each mechanism applies to. The product (A) gets all of them; B and C get the proportionate set that avoids a slow week, not a lost minute; X carries the product’s mechanisms where it sits in the product’s path.
Notes: Slide 4: Resilience toolkit
Five nines ≈ 5 minutes a year; argued from content; board’s risk appetite; no SLA in source
No single mechanism gets you there
1 Isolate · 2 Replicate · 3 Release safely · 4 Detect and respond · 5 Protect content
Hub and spoke: sync spokes (authoring, identity, third-party APIs); async behind the bus (CRM, shop, finance, reporting)
Proportion: B and C get the set that stops a slow week, not a lost minute
Cost sits where the risk is
Story: life-critical availability (EMIS)

## Slide 5
5 · PUBLISHING AND ROLLBACK INSIDE THE PRODUCT
One publishing hub, regional nodes that serve alone, rollback by re-pointing
ILLUSTRATIVE — NOT A DECISION
Publishing hub
authoring → review → approve
build → test evidence → sign
release manifest
{content vN, code vN}
Event log
as proposed: the bus
immutable, ordered,
retained, replayable
fan-out to every node
publish
Region 1
primary for its users
content vN · app · entitlement cache
serves alone if the hub is down
Region 2
primary for its users
content vN · app · entitlement cache
serves alone if the hub is down
Region 3
standby; rebuilt from the log
content vN · app · entitlement cache
serves alone if the hub is down
nodes are backups
for each other
Multi-CDN edge
published content cached at the edge
anycast DNS and health-based routing to the nearest healthy node
clinicians, institutions,
third-party systems
ROLLBACK IN THIS WORLD
Rolling back is re-pointing to vN-1 — seconds, no redeploy
Content and code roll back together: the manifest binds them
A lost node is rebuilt by replaying the log — no restore from backup
Canary: publish to one node or cohort, watch the SLO, then fan out
OTHER CONSIDERATIONS — TO EVALUATE, NOT CHANGES
Event backbone: replay and ordering
Kafka-class log
Institutional single sign-on
Shibboleth / SAML
Learning-platform integration
LTI / LIS
Clinical and prescribing systems
clinical standards
Information security management
ISMS / ISO 27001
Clinical publishing governance
provenance, errata
Notes: Slide 5: Publishing and rollback
Second hub and spoke: inside the product
Hub → manifest (content vN + code vN) → event log → nodes
Log: immutable, ordered, retained, replayable; requirements not a product choice
Nodes serve alone; Region 3 rebuilt from log; multi-CDN edge, health-based routing
Rollback = re-point to vN-1, seconds, no redeploy
Consideration, not a decision: managed Kafka-class log

## Slide 6
6 · THE TEAM THE NEXT STAGE NEEDS
A minimum viable team of six
ILLUSTRATIVE — NOT A DECISION
MINIMUM VIABLE TEAM — WHO OWNS WHAT
CTO
Strategy, architecture, transformation, project management, roadmap
vs proposal: tweaked responsibilities
A
B
C
X
Technical Lead
Standards, build, maintain, technical QA
A
X
B
Developer
Build, maintain, technical QA
vs proposal: new — replaces the 0.6 PM
A
X
Platform Engineer (DevSecOps)
Security, ISMS, platform, pipeline
vs proposal was DevOps Engineer;
X
A
B
Digital Product Owner
Project, research, design
vs proposal research, design added
A
B
C
QA / BA
User testing, QA, product assistance
vs proposal was part-time BA; QA made focus
A
C
OPTIONS GATE 2 WOULD CHOOSE BETWEEN
Second Developer, or the vendor’s 0.6 PM
how much of the product is built in-house
AI budget and AI-DLC adoption instead of more headcount
assist, accelerate and de-risk product work
NOT IN THE TEAM — PARTNER OR MSP
Responsibilities, not an approved hiring plan.
Managed service provider — office IT
Laptops, printers, phones and internet
Specialist partners — bought in when needed
Independent security testing and certification
Expert help on vendors’ systems (CRM, shop, finance)
Outside the team’s remit
Content operations
Notes: Slide 6: The team
Worked backwards from tiers and CTO remit
Six: CTO · Technical Lead · Developer (replaces 0.6 PM) · Platform Engineer (DevSecOps) · Digital Product Owner · QA/BA
Why: Tier A needs two pairs of hands; key-person risk; PM sits with CTO; QA evidence for gates
Now = the six · Over time = second developer or vendor 0.6 PM; AI budget and AI-DLC instead of headcount · Source = MSP, specialist partners, vendor experts
Content operations outside remit
Own judgement, not headcount; partners decide how
Story: partner or MSP; thin team (EMIS India, CallCredit Lithuania)

## Slide 7
7 · GOVERNANCE, ASSURANCE GATES AND THE NEXT SIX MONTHS
One operating rhythm, gates sized to the tier, judged on outcomes rather than AI activity
OPERATING RHYTHM — WHO SEES WHAT
Board / Risk Committee
quarterly, with a monthly review pack · date confidence, gate sign-off, risks, spend
Delivery and Partner Review
weekly, CEO invited · cycle time, change failure, blockers, decisions pending
Architecture decisions
written down, visible to all
ASSURANCE GATES BY TIER — EVERY INCREMENT, EVIDENCE NOT MEETINGS
A
B
C
X
Security, payments and ISMS
Data and privacy
Content integrity and clinical governance
Integration and operability
Release readiness
A product · B content tooling · C commodity · X cross-cutting
THE NEXT SIX MONTHS
Months 1–2
two baselines, fit test, scope decisions to the board
Months 3–4
first assured delivery on the core; partners delivering
Months 5–6
build waves, cutover rehearsal, go-live against the date
Notes: Slide 7: Governance and six months
Board/Risk quarterly + monthly pack · weekly Delivery and Partner Review, CEO invited · architecture decisions written down · no separate steering layer
Five gates: security/payments/ISMS · data/privacy · content integrity/clinical governance · integration/operability · release readiness
Inward: cycle time, change failure, rework, recovery. Upward: date confidence, availability vs appetite, risks, spend, decisions pending. AI on cycle time and quality, not tokens
Months 1–2 baselines, fit test, scope to board · 3–4 first assured delivery · 5–6 build waves, rehearsal, go-live
Tell the Board: fixed date so scope flexes · team of six · budget to confirm · vendor dependency · content ops capacity · availability and payments across every channel

## Slide 8
8 · IDEAS BEYOND DAY 1
Not commitments, not walked through today — parked until their time comes
DAY 1.5 — IDEAS WALL: PARKED, UNSORTED, JUDGED BY TIER WHEN THEIR TIME COMES
Unified communications
Product analytics and behaviour
In-app guidance and onboarding
Inline surveys and sentiment
Feature switches, progressive delivery
Search as a product capability
Developer and API portal
Consent and preferences
Status page and incident comms
Integration standards: SSO, LTI/LIS, clinical
Content versioning visible to customers
Accessibility and offline mobile
DAY 2 — ALREADY ON THE PATHWAY
Assistant over authoritative content — citations, no generated clinical text
Internal operational AI on the same platform
Subscription and user-update integration
Yellow product · orange cross-cutting · green content tooling. Day 1.5 = after the agreed path is live, before Day 2.
Notes: Slide 8 and close
Don’t walk the wall: “what the proposal doesn’t show yet; judged by tier; no commitments”
Day 1.5: analytics, consent, status page, integration standards, content versioning
Day 2: assistant over authoritative content, citations, no generated clinical text; governance first
Close: customers, revenue, content integrity intact · core live and bullet-proof · commodity cheap and quiet · decisions written down · Day 2 ready with guardrails set