Slide 1: Own it without stalling it

- Pathway agreed, date fixed: own it, don’t stall it

- Publishing model → digital product platform; pivot agreed, shape and ways of working not

- Understand 1–30 (two baselines) · Stabilise 31–60 (keep running, assess proposal, confirm/re-scope/stop) · Accelerate 61–90→ (first assured delivery, plan to date)

- Rule 1: nothing that works stops until replacement proven. Rule 2: nothing starts without owner and gate

- Say it: everything after this is a hypothesis; Gates 1 and 2 test it

Story: inherited mid-flight

Bridge: “Here’s that on the calendar.”

Slide 2: 90 days vs 27 April

- December start; break eats 3 of first 4 weeks; Gate 1 mid-Jan; baselines = a fortnight

- Day 90 early March; about 8 working weeks to go-live

- G1 day 30: two baselines → one-page baseline, in-flight list

- Why two: proposal = technology and products, not how we work; savings live there

- G2 day 60: fit test (supports how we work? right tier, right rule?) → the plan we’re held to. Builds on Phase 1 assurance review

- G3 day 90: first assured delivery (identity and entitlement, or content pipeline)

- Not in 90 days: commit to architecture, migrate data, extra hires, refined date or cost, AI platform before governance

- Scope is the only lever; trade-off to board at G2, late Jan, in writing

Story: fixed date

Bridge: “Next three slides: one credible shape the assessment would weigh, not the answer.”

Slide 3: Four tiers, four questions

- Four questions: what kind of thing / spending judged on / how resilient / build or buy

- A product (AMH Online): moat · commercials · bullet-proof · build

- B content tooling (Quark, PriXM): content is the asset · fit, portability, cost · business hours, never only copy · buy and configure

- C commodity (D365, shop, Wiise, Power BI): cost vs efficiency · standard, no shared fate · buy, exceptions only

- X cross-cutting (identity, bus, monitoring, ISMS): inherits A’s posture · buy, bend to A

- AI: A accelerates · B assists, human sign-off · C woven in (Excel pricing step) · X triage and runbooks

- Guardrail: no AI output to content or production without a human gate

Story: commodity over build (CRM)

Slide 4: Resilience toolkit

- Five nines ≈ 5 minutes a year; argued from content; board’s risk appetite; no SLA in source

- No single mechanism gets you there

- 1 Isolate · 2 Replicate · 3 Release safely · 4 Detect and respond · 5 Protect content

- Hub and spoke: sync spokes (authoring, identity, third-party APIs); async behind the bus (CRM, shop, finance, reporting)

- Proportion: B and C get the set that stops a slow week, not a lost minute

- Cost sits where the risk is

Story: life-critical availability (EMIS)

Slide 5: Publishing and rollback

- Second hub and spoke: inside the product

- Hub → manifest (content vN + code vN) → event log → nodes

- Log: immutable, ordered, retained, replayable; requirements not a product choice

- Nodes serve alone; Region 3 rebuilt from log; multi-CDN edge, health-based routing

- Rollback = re-point to vN-1, seconds, no redeploy

Consideration, not a decision: managed Kafka-class log

Slide 6: The team

- Worked backwards from tiers and CTO remit

- Six: CTO · Technical Lead · Developer (replaces 0.6 PM) · Platform Engineer (DevSecOps) · Digital Product Owner · QA/BA

- Why: Tier A needs two pairs of hands; key-person risk; PM sits with CTO; QA evidence for gates

- Now = the six · Over time = second developer or vendor 0.6 PM; AI budget and AI-DLC instead of headcount · Source = MSP, specialist partners, vendor experts

- Content operations outside remit

- Own judgement, not headcount; partners decide how

Story: partner or MSP; thin team (EMIS India, CallCredit Lithuania)

Slide 7: Governance and six months

- Board/Risk quarterly + monthly pack · weekly Delivery and Partner Review, CEO invited · architecture decisions written down · no separate steering layer

- Five gates: security/payments/ISMS · data/privacy · content integrity/clinical governance · integration/operability · release readiness

- Inward: cycle time, change failure, rework, recovery. Upward: date confidence, availability vs appetite, risks, spend, decisions pending. AI on cycle time and quality, not tokens

- Months 1–2 baselines, fit test, scope to board · 3–4 first assured delivery · 5–6 build waves, rehearsal, go-live

- Tell the Board: fixed date so scope flexes · team of six · budget to confirm · vendor dependency · content ops capacity · availability and payments across every channel

Slide 8 and close

- Don’t walk the wall: “what the proposal doesn’t show yet; judged by tier; no commitments”

- Day 1.5: analytics, consent, status page, integration standards, content versioning

- Day 2: assistant over authoritative content, citations, no generated clinical text; governance first

- Close: customers, revenue, content integrity intact · core live and bullet-proof · commodity cheap and quiet · decisions written down · Day 2 ready with guardrails set